AI Resource Center · Domain 5 — Student Support & Success

Domain Group Meeting — Agenda

Thursday, June 18, 2026  ·  1:00 PM AZ (confirm 1:00 vs 2:00 PM, and that it works for the member who teaches Thursday)

Goal of this meeting: move from discussion to assignments. Approve the plan, form subcommittees, and leave with named owners (by sign-up) and first deliverables.

# 1 · What's changed since May 21 (5 min)

Since the last meeting we built a working foundation that supersedes our prior open items:

- An ARC-aligned domain plan (four prioritized initiatives + roadmap + execution paths).

- A Student Journey study kit - 3 personas, a branching task roadmap (problems, not destinations), and a service crosswalk across all 10 colleges.

- Grounded in real data - the GCC Faculty Senate Frustrations Survey (83 barriers, ~4.5/5 frustration & impact) and the Rio Salado Student Senate notes, both cross-walked into the tasks.

- Swirling built in - two personas enroll at a second college (second application, residency re-proof, consortium aid).

- A flagship AI build identified - an AI Canvas Course Barrier Checker (OSCQR + required syllabus elements).

# 2 · Decisions to make today (15 min)

- Approve the four-initiative plan and the Fall 2026 fieldwork timeline   (5)

- Approve forming the subcommittees below (incl. Salesforce Discovery, proposed last meeting)   (4)

- Confirm the tester-form route so data collection can start   (3)

- Decide whether to pursue funding for a friendly AI well-being/buy-in item (the 'AI stress ball' idea)   (3)

# 3 · Subcommittee assignments & objectives (20 min)

Members sign up for one or two. Each names a lead, has a clear objective, and brings a first deliverable to the next meeting. Students (incl. design-studio students and the Student AI Group) can join and drive parts.

| Subcommittee | Objective | First deliverable / when |
| --- | --- | --- |
| UX Study & Crosswalk | Run the Student Journey study: confirm one rep per college, verify each college's crosswalk column, recruit design-studio students to run personas, stand up the tester form, and dry-run with one college. | Reps confirmed + verified crosswalk + working form · fieldwork Fall 2026 |
| Salesforce Discovery | Find out exactly what the un-purchased Salesforce admissions bot does, whether it can be modified to NOT collect student data, and whether Salesforce can verify ID/residency ONCE across campuses (cuts swirling barriers). Meet with Sonal + Salesforce. | Findings memo + recommendation (build / modify / decline) · 3-4 weeks |
| Student AI Literacy (joint) | Design a class-level Canvas AI-expectations module/button (faculty set rules + concrete examples), scale the GBS233 Digital Literacy module, and create short AI-literacy lessons. Schedule joint sessions with overlapping ARC committees. | Literacy plan + joint-session calendar · 4-6 weeks |
| Course Quality / Canvas Checker | Scope the AI Canvas Course Barrier Checker against OSCQR + required syllabus elements (SyllabusPlus), and design faculty incentives (participation can't be mandated). | Pilot scope + incentive plan · 4-6 weeks |
| Financial Aid & Retention | Scope a financial-aid/retention assistant (basic FA questions; veteran drop/refund/academic-warning; proactive 'if I drop, what happens to my aid'). Research why students drop out (Dean of Students + national data). | Bot scope + dropout-reasons summary · 4-6 weeks |
| Student Partnership & Buy-in | Stand up the Student AI Group via student government (offer civic-duty/volunteer credit). Bring a proposal + budget for a friendly AI well-being/buy-in item modeled on the accessibility stress ball. | Recruitment plan + well-being/mascot proposal · 4 weeks |

# 4 · Action items (10 min)

| Action | Owner (sign-up) | By |
| --- | --- | --- |
| Confirm one representative per college | Co-chairs | Jun 30 |
| Sign up for subcommittees + name a lead for each | All members | Today |
| Decide tester-form route and start the form | Co-chairs | This week |
| Identify Salesforce/Sonal + IT contacts | Co-chairs | Jul 15 |
| Find national dropout data (start: NSC Research Center, CCSSE) | FA & Retention subcommittee | 3 weeks |
| Bring a well-being/mascot funding ask to next meeting | Student Partnership subcommittee | Next mtg |
| Confirm fall meeting cadence | Co-chairs | Jun 30 |

# 5 · Parking lot — routed, not dropped (5 min)

- Which committees for joint AI-literacy sessions? -> Student AI Literacy subcommittee to propose.

- How to get Salesforce admissions-bot detail + modification? -> Salesforce Discovery.

- National data on why students drop out? -> Financial Aid & Retention.

- Advising bot caution (advising is too nuanced) -> scope only low-level FAQ after a student's first advising appointment, under FA & Retention / UX findings.

- Funding for a friendly AI item? -> decision above + Student Partnership subcommittee.

# Project timeline (high level)

Realistic sequencing. Most people are away over summer, so fieldwork starts in fall.

| Phase | Window | Focus |
| --- | --- | --- |
| Discovery & setup | Summer 2026 | Finalize the study kit, recruit testers (employees role-playing, student government, work-study, design-studio students), pilot the tool. Setup and recruiting only while people are away. |
| Fieldwork | Fall 2026 | Run the personas across colleges; assigned SSS team members and students log barriers through the form. |
| Synthesis | Winter 2026-27 | Affinity-map findings, build the AI Opportunity Map, severity-rank the barriers. |
| Recommendations & case study | Spring 2027 | Prioritized AI recommendations and pilots; a presentable case study by spring break. |
| Present | May 2027 | Share the work at conferences. |

# 6 · Next steps & close (5 min)

- Each subcommittee schedules its first working session and names a lead.

- Co-chairs circulate the plan + study kit and confirm fall cadence.

Reminder: this domain only makes AI-related recommendations; service-process ideas get routed to the appropriate body.